Stakeholder & Communication Plan

Stakeholder Identification

The stakeholders identified below are based on their influence over pricing, product profitability, regional sales performance, analytical decision-making, and implementation of the recommendations identified during the analysis.

| Stakeholder | Role In analysis | Interest | Influence |
| --- | --- | --- | --- |
| Business Management | Reviews overall business performance and approves strategic actions | High | High |
| Pricing/Commercial Team | Manages pricing and discount strategies | High | High |
| Product Management | Owns product performance and product-level decisions | High | High |
| Regional Sales Team | Manages regional sales and discount practices | High | Medium |
| BI / Analytics Team | Supports reporting, dashboards, and ongoing monitoring | Medium | Medium |

Stakeholder Communication Matrix

Stakeholder Communication Plan

The communication plan defines the information required by each stakeholder, the appropriate communication method, and the decisions or actions expected from them. Communication will focus on business impact, evidence-based findings, recommendations, and agreed actions rather than technical SQL outputs alone.

| Stakeholder | Key Information Required | Communication Method | Expected decision / Action |
| --- | --- | --- | --- |
| Business Management | Overall sales, profit, margin, key profitability drivers, recommendations | Management presentation / Dashboard | Approve priorities and strategic actions |
| Pricing / Commercial Team | Discount exposure, discount-profit relationship, Tables profitability | Analytical report / Review meeting | Review discount thresholds and pricing strategy |
| Product Management | Loss-making Tables products, product margins, discount exposure | Product performance report / Dashboard | Identify products requiring pricing or commercial intervention |
| Regional Sales Team | Regional sales, profit, margin, discount exposure | Regional performance review | Investigate regional discount practices |
| BI / Analytics Team | KPI definitions, dashboard requirements, data limitations | Requirements document / Working session | Implement and maintain the profitability monitoring dashboard. |

Stakeholder Power-Interest Assessment

Stakeholders are assessed based on their level of influence over business decisions and their level of interest in the analysis outcomes. The assessment is used to determine the appropriate level of stakeholder engagement and communication.

| Stakeholder | Power | Interest | Engagement Strategy |
| --- | --- | --- | --- |
| Business Management | High | High | Manage Closely |
| Pricing/Commercial Team | High | High | Manage Closely |
| Product Management | High | High | Manage Closely |
| Regional sales Team | Medium | High | Keep Involved |
| BI / Analytics Team | Medium | Medium | Collaborate / Keep Informed |

Communication Frequency

Communication frequency is determined based on stakeholder influence, level of interest, decision urgency, and the expected rate of change in the relevant business metrics. Higher-priority stakeholders and stakeholders directly involved in corrective actions will receive more frequent updates during implementation.

| Stakeholder | Recommended Frequency | Purpose |
| --- | --- | --- |
| Business Management | Monthly / Key Decision Meetings | Review profitability performance, major findings, and strategic actions |
| Pricing / Commercial Team | Bi-Weekly during interventions | Review discount exposure, pricing decisions, and profitability impact |
| Product Management | Bi-Weekly during product review | Track loss-making products and agreed product-level interventions |
| Regional Sales Team | Monthly | Review regional discount exposure, sales, and profitability |
| BI / Analytics Team | Weekly during dashboard development; monthly after implementation | Track dashboard requirements during development and ongoing monitoring after implementation |

Communication Principles

The following principles will guide stakeholder communication throughout the project to ensure that information is clear, relevant, evidence-based, and aligned with stakeholder responsibilities.

1. Business-Focused Communication

Findings will be communicated in terms of business impact, decisions, and actions rather than technical SQL outputs alone.

2. Evidence Based Communication

Business conclusions will be supported by validated analytical evidence, with assumptions and interpretations clearly distinguished from confirmed findings.

3. Audience-Specific Communication

The level of detail and communication format will be tailored to the stakeholder's role, decision-making responsibility, and analytical requirements.

4. Transparent Data Limitations

Known data limitations, including the 300-record source-to-database discrepancy and unavailable operational variables, will be communicated clearly when they may affect interpretation or decision-making.

5. Action-Oriented Communication

Significant findings will be translated into clear recommendations, decisions, or follow-up actions where appropriate.

6. Traceability

Key findings, recommendations, and actions will remain traceable to the underlying analysis and documented business requirements.